| Progress Report of the One South Lakeland Partnership Board, Task & Finish Groups From October 2011 to January 2012 Friday 20th January 2012, 10.00 am |  |
| --- | --- |

| Task & Finish Group | Lead/Org | Comment | Status |
| --- | --- | --- | --- |
| Community Engagement | Julia Wilson, ACT | Developed and agreed action plan at first meeting, Second meeting planned for January with progress achieved at stage 1 with visits to LAP meetings by officers. Progress update to be prepared for March meeting, | ( |
| Sustainability & Climate Change | Layla Newby, SLDC | Developed & agreed action plan with first meeting planned to discuss the Strategic Framework in February. Report on progress for March meeting | ( |
| Health & Wellbeing | TBA | Currently this work is on hold until people and structures are established based on the new White Paper. | ( |

| Groups already established | Lead/Org | Comment | Status |
| --- | --- | --- | --- |
| Diverse Employment | Jayne Kendall, SLDC | This work is being delivered through a number of channels, Business Forums and the launch of the Invest in South Lakeland website mostly, see attached report for detail. It is not proposed that this work will be monitored by the OSLB | ( |
| Homes to meet Need | SLDC | This work is being delivered through the Housing Advisory Group in partnership with Eden DC, see attached action plan. It is not proposed that this work will be monitored by the OSLB | ( |
| Reduce Crime & anti-social behaviour | Community Safety Partnership | This work is being delivered through the Community Safety Partnership in collaboration with Barrow BC, see attached report for detail. It is not proposed that this work will be monitored by the OSLB | ( |
| Transport | Cumbria County Council | Update to be provided by the March meeting |  |

Progress:

On Track = (

Likely to be delayed temporarily = (

Delayed (Board intervention needed) = (