Local Community Engagement Task & Finish Group

Programme of work

- Goals for the period to 31st March 2013

Participatory budgeting is successfully piloted in one area in South Lakeland Local groups are fully involved in the pilot A range of public sector agencies are involved in the pilot including SLDC, the PCT and the Police

Public sector agencies in South Lakeland are challenged to strengthen their ‘engagement culture’ Local agencies advised, monitored and challenged to strengthen engagement with their local communities

- Actions for the period to 31st March 2012

Julia Wilson (ACT) was nominated Chair of the group.  It was agreed that the group will meet monthly until March 2012, when the next phase will be developed. The following actions were agreed for completion by 31st March 2012.

2.1 Piloting participatory budgeting - Lead officer, John Dyer, SLDC

Stage 1

| What? | Who? | When? |
| --- | --- | --- |
| One-to-one support visits to parishes and LAPS to build understanding | JFD | 31 Jan 12 |
| Identify how to involve stakeholders (including defining an evaluation process) prepare paper for December T&F Group meeting | JT | 31 Dec 11 |
| Identify how intelligence and data will be disaggregated to organisations | JFD | 31 Jan 12 |
| Complete evaluation of bids including discussion at the T&F Group | JFD | 28 Feb 12 |

Stage 2

| What? | Who? | When? |
| --- | --- | --- |
| Complete ‘get to know you sessions’ with the selected locality | JFD | 28 Feb 12 |
| Establish the local steering group | JFD | 28 Feb 12 |
| Prepare a focussed communications plan (including initial publicity and the launch of the project) for discussion at the T&F Group | JFD | 31 Mar 12 |

Stage 3

| What? | Who? | When? |
| --- | --- | --- |
| Prepare detailed programme (PID) including vision, benefits, outcomes, resources, responsibilities and communication | JDF | April 12 |
| Begin implementation | JDF | April 12 |

2.2 Strengthening the ‘engagement culture’ – Lead officer, Jayne Thorp, PCT

| What? | Who? | When? |
| --- | --- | --- |
| Agree a concise ‘participatory framework’ setting out the principles and practices of community engagement prepare proposal for next T&F Group meeting | EN | 31 Jan 12 |
| The Task and Finish Group to meet to review of all community facing strategies and identify specific recommendations for improving community engagement prepare overview of strategies for next T&F Group meeting | EN | 31 Jan 12 |
| Establish a Community Engagement Forum; bringing together professionals working on community engagement, creating a single database of good practice and promoting examples of good practice prepare draft brief for the Engagement Forum for discussion at the T&F Group | JT | 28 Feb 12 |
| Encourage community-led planning groups to take finished plans to LAPS | JW | 31 Mar 12 |

Members of the Task and Finish Group

The following members attended the first meeting of the Task and Finish Group help on 10th November 2011.

| Name | Organisation | Email |
| --- | --- | --- |
| Emma Nichols | SLDC | e.nichols@southlakeland.gov.uk |
| Janette Jenkins | South Lakeland CALC | JEJenky@aol.com |
| Cath Davenport | S. Westmoreland LAP | cmadavenport@hotmail.com |
| Sonia Mangan | Age UK South Lakeland | smangan@ageuksouthlakeland.org.uk |
| John Dyer | SLDC | j.dyer@southlakeland.gov.uk |
| Julia Wilson | ACT | juliawilson@cumbriaaction.org.uk |
| Jayne Thorp | PCT | Jayne.thorp@cumbriapct.nhs.uk |